Meeting Minutes

Date:	10/10/18				Location: NCB

Start Time:	5:00			End Time: 6:30

Attendees: Billy Petrakes, Bassam Ghali, Leon Diec, Jay Aliaga

Absent:

Topic: Fundraising for Prizes

Pre-meeting Materials for Review: (Provide title and location)

- Previous Minutes

Agenda:

- Summary of progress

- Plan for fundraising from local restaurants

Description of Activities: As a group, we solidified the idea for the cornhole tournament. We discussed that prizes for the tournament would be vital for participation.

We contemplated the best method to get participation from local restaurants. After discussion, we decided email requests would be the best way to gain interest quickly. Bassam drafted an informative email template that the group will use to send out to each bar or restaurant. We gathered the contact information and divided up who was responsible for each restaurant. Each email will contain the information flyer that Erin provided last meeting.

Some locations had designated emails but others had limited contact info.

Action Items: Each member was responsible for contacting 3-4 restaurants. 10/11 date is by when we should send out emails.

| What | Who | By When |
| --- | --- | --- |
| Cellar, She Sha Café, Sycamore Deli | Leon Diec | 10/11 |
| Lefty’s, Taphouse, 622 North | Bassam Ghali | 10/11 |
| Stakeholder Registry and main contact with Erin | Billy Petrakes | 10/11 |
| Rivermill, Hokie House, Pk’s, Benny’s, Ceritanos | Jay Aliaga | 10/11 |

Unresolved Issues:

The following restaurants did not have direct emails. Shall require in person follow if necessary:

Our daily bread

El rods

Carol Lees

Mellow mushroom (forum on website)

Next door bake shop

Himalayan cafe